## Project Completeness
Overall Progress Report for NHLBI Contract - Weekly Report Sent on Fridays | [6 empty] | Completeness of the Project (%) |  |  |  | 0
Contract # | HHSN# |  |  |  | CORE Year # |  | Total # of samples approved |  |  |  | 9999
Center Name | ABC Omics |  |  |  | Form Ver 3.1 |  | Total # of samples completed |  |  |  | 0
Week of | 2019-12-31
Cohort/Study | MTA needed? | MTA in place? | Expected Date of First Shipment | Expected Date of Final Shipment | Approved Sample Number | Total Samples Received To Date | Visual QC Fail | Sample Volume Fail | Samples Aliquoted | LC-MS Method | Sample Intake | Samples Analyzed | Samples Run Per Column | Samples Completed QC | Samples Flagged for Re-analysis | Failed Post-Processing QC (will not re-attempt) | Sample Profiles Awaiting Transmission | Sample Profiles Transmitted | Expected Profile Submission Completion Date
Study 1 | no | N/A | 2019-02-22 | TBD | 3000 | 2118 | 0 | 0 | 2118 | C8-pos (Broad) | 2118 | 2118 | (1) 1100 (2) 1018 | 2118 | 3 | 5 | 0 | 0 | Est. 7/31/19
[10 empty] | C18-neg (Broad) | 2118 | 0 |  | 0 | 0 | 0 | 0 | 0 | Est. 7/31/19
[10 empty] | HILIC-pos (Broad) | 2118 | 0 |  | 0 | 0 | 0 | 0 | 0 | Est. 7/31/19
[10 empty] | Amide-neg (BIDMC) | transfer planned for week of 3/25/19 | 0 |  | 0 | 0 | 0 | 0 | 0 | Est. 7/31/19
Study 2 | no | N/A | 2019-03-25 | 2019-03-25 | 3400 | 0 | 0 | 0 | 0 | C8-pos (Broad) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Est. 10/31/19
[10 empty] | C18-neg (Broad) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Est. 10/31/19
[10 empty] | HILIC-pos (Broad) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Est. 10/31/19
[10 empty] | Amide-neg (BIDMC) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Est. 10/31/19
Study 3 | no | N/A | Estimate: April 12 | NA | 1400 | 0 | 0 | 0 | 0 | C8-pos (Broad) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Est. 12/15/19
[10 empty] | C18-neg (Broad) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Est. 12/15/19
[10 empty] | HILIC-pos (Broad) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Est. 12/15/19
[10 empty] | Amide-neg (BIDMC) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Est. 12/15/19
Total |  |  |  |  | 7800 | 2118 | 0 | 0 | 2118 | 0 | 6354 |  |  | 2118 |  |  | 0 | 0
Outstanding or Critical Issues:
1. Firm dates for receipt of Study 2 samples and the balance of samples for the asthma study are pending.
2. We have aliquted a sufficient number of Study 3 samples to begin the asthma study. We request permission to proceed with the analyses.

## Metrics Definitions
Metric Name | Metric definition
Expected Date of First Shipment | first sample shipment date provided by repositiory
Expected Date of Final Shipment | final shipment date provided by repository
Approved Sample Number | Number of samples approved for metabolite profiling analyses by NIH
Total Samples Received To Date | Total number of samples received by the Broad Institute as of the report date
Visual QC Fail | Number of samples determined to be problematic (e.g. missing samples, thawed samples, excessive hemolysis, other)
Sample Volume Fail | Number of samples of inadequate volume for complete analysis
Samples Aliquoted | Number of samples of inadequate volume for complete analysis
LC-MS Method | Name of one of four profiling methods being applied
Sample Intake | Number of samples aliquoted for each specific method
Samples Analyzed | Number of samples analyzed in the LC-MS method as of the date of the report
Samples Analyzed per Column | Samples Analyzed per Column - note in project completion if column is shared between cohorts
Samples completed QC | Number of samples that have been reviewed for quality while in process
Samples flagged for re-analysis | Number of samples that did not pass in process QC that are flagged for re-analysis
Failed post-processing QC (will not re-attempt) | Number of samples identified as failing QC after completion of profiling and data processing
Sample Profiles Awaiting Transmission | Number of samples for which raw data has been acquired and processed but for which results have yet to be reported
Sample Profiles Transmitted | Number of samples for which for which results have been reported
Expected Profile Submission completion date | Expected date by which all data will be reported.

## Project Averages
Project | LC-MS Method | # identified metabolites | # of unidentified peaks | QC
|  |  |  | Median CV identified metabolites | Median CV unidentified peaks
Study 1 | C8-pos (Site)
C18-neg (Site)
HILIC-pos (Site)
Amide-neg (Site)
Study 2 | C8-pos (Site)
C18-neg (Site)
HILIC-pos (Site)
Amide-neg (Site)
Study 3 | C8-pos (Site)
C18-neg (Site)
HILIC-pos (Site)
Amide-neg (Site)

## Doc Versioning
Authored by GJP
Original version by George J Papanicolaou, PhD
Version Changes
3.1 Edits and reviewed -gjp 3/27/2019
3.0 Formatted for metabolomics -cbc- 3/12/2019
2.0 Added example reports, provided additonal production metrics, and introduced Project Averages tab -gjp- 6/29/2017
1.0 Released 2/10/2017